## PS PH 3 Draw Sheet
WEBER COUNTY ESCROW
Site Improvements
| The Bridges - Parkside Phase 3 | [13 empty] | Note - the Cumulative Complete needs to carry forward (add manually) to each Draw column. Then add next % complete at the next Draw
Eden, Utah
[7 empty] | As of 11/15/22 |  |  |  |  | Draw # 1 |  |  | Draw # 2 |  |  |  |  | Draw # 3 |  |  |  |  | Draw # 4 |  |  |  |  | Draw # 5 |  |  |  |  | Draw # 6
[7 empty] | CUMULATIVE $$ | % |  |  | % | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining
| ROAD & ROW GRADING AND EXCAVATION | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | COMPLETED | COMPLETE | ESCROW AMT |  | Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance
1 | Roadway Cut / Excavation | 656 | cy | 8.6 | cy | 5641.6 | 5642 | 100% | -0.4 | 100% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4
2 | Embankment Cut / Excavation | 656 | cy | 7.2 | cy | 4723.2 | 4723 | 100% | 0.2 | 100% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2
3 | Import Fill For Embankment | 1715 | ton | 16.18 | ton | 27748.7 | 27749 | 100% | -0.3 | 100% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3
4 | Furnish and Install 3" thick Asphalt Paving | 25068 | sf | 1.9 | sf | 47629.2 | 0 | 0% | 47629.2 | 100% | 0% | 0 | 100% | 47629.2 | 0% | 0% | 0 | 100% | 47629.2 | 0% | 0% | 0 | 100% | 47629.2 | 0% | 0% | 0 | 100% | 47629.2 | 0% | 0% | 0 | 100% | 47629.2 | 0% | 0% | 0 | 100% | 47629.2
5 | Furnish and Install 6" Road Base (includes grading) | 1013 | ton | 19.27 | ton | 19520.51 | 19521 | 100% | -0.49 | 100% | 0% | 0 | 100% | -0.49 | 0% | 0% | 0 | 100% | -0.49 | 0% | 0% | 0 | 100% | -0.49 | 0% | 0% | 0 | 100% | -0.49 | 0% | 0% | 0 | 100% | -0.49 | 0% | 0% | 0 | 100% | -0.49
6 | Furnish and Install 9" Sub-base Material (includes grading) | 1156 | ton | 18.2 | ton | 21039.2 | 21039 | 100% | 0.2 | 100% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2
7 | Curb and Gutter | 689 | lf | 19.8 | lf | 13642.2 | 13642 | 100% | 0.2 | 100% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2 | 0% | 0% | 0 | 100% | 0.2
| ROAD & ROW GRADING AND PAVING |  |  |  | TOTAL | 139944.61 | 92316 |  | 47628.61 |  |  | 0 |  | 47628.61 |  |  | 0 |  | 47628.61 |  |  | 0 |  | 47628.61 |  |  | 0 |  | 47628.61 |  |  | 0 |  | 47628.61 |  |  | 0 |  | 47628.61
| STORM DRAINAGE | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 15" RCP Storm Drain | 458 | lf | 130 | lf | 59540 | 59540 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
2 | Furnish and Install 24" x 48" Concrete Catch Basin | 5 | ea | 2755 | ea | 13775 | 13775 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
| STORM DRAIN |  |  |  | TOTAL | 73315 | 73315 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
| SECONDARY WATER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 10" PVC C900 Water Line | 274 | lf | 36.55 | lf | 10014.7 | 10015 | 100% | -0.3 | 100% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3 | 0% | 0% | 0 | 100% | -0.3
2 | Furnish and Install 8" Gate Valve | 5 | ea | 2471 | ea | 12355 | 12355 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Secondary Fittings | 2 | ea | 1717 | ea | 3434 | 3434 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Furnish and Install 4" Drain Valve | 2 | ea | 1769 | ea | 3538 | 0 | 0% | 3538 | 100% | 0% | 0 | 100% | 3538 | 0% | 0% | 0 | 100% | 3538 | 0% | 0% | 0 | 100% | 3538 | 0% | 0% | 0 | 100% | 3538 | 0% | 0% | 0 | 100% | 3538 | 0% | 0% | 0 | 100% | 3538
5 | Temporary Blow Off | 2 | ea | 1248 | ea | 2496 | 0 | 0% | 2496 | 100% | 0% | 0 | 100% | 2496 | 0% | 0% | 0 | 100% | 2496 | 0% | 0% | 0 | 100% | 2496 | 0% | 0% | 0 | 100% | 2496 | 0% | 0% | 0 | 100% | 2496 | 0% | 0% | 0 | 100% | 2496
6 | Connect to Existing Main | 2 | ea | 1381 | ea | 2762 | 2762 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
7 | Collar Valves | 4 | ea | 435 | ea | 1740 | 0 | 0% | 1740 | 100% | 0% | 0 | 100% | 1740 | 0% | 0% | 0 | 100% | 1740 | 0% | 0% | 0 | 100% | 1740 | 0% | 0% | 0 | 100% | 1740 | 0% | 0% | 0 | 100% | 1740 | 0% | 0% | 0 | 100% | 1740
| SECONDARY WATER |  |  |  | TOTAL | 36339.7 | 28566 |  | 7773.7 |  |  | 0 |  | 7773.7 |  |  | 0 |  | 7773.7 |  |  | 0 |  | 7773.7 |  |  | 0 |  | 7773.7 |  |  | 0 |  | 7773.7 |  |  | 0 |  | 7773.7
| SANITARY SEWER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 8" SDR-35 Sewer Main | 871 | lf | 38.55 | lf | 33577.05 | 33577 | 100% | 0.05 | 100% | 0% | 0 | 100% | 0.05 | 0% | 0% | 0 | 100% | 0.05 | 0% | 0% | 0 | 100% | 0.05 | 0% | 0% | 0 | 100% | 0.05 | 0% | 0% | 0 | 100% | 0.05 | 0% | 0% | 0 | 100% | 0.05
2 | 4" Sewer Laterals off 8" Main | 16 | ea | 965 | ea | 15440 | 15440 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Furnish and Install 4' Diameter Manhole - Precast | 5 | ea | 3813 | ea | 19065 | 19065 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Clean / Flush / Test Video | 871 | ea | 1.5 | ea | 1306.5 | 1307 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
5 | Collar Valves | 3 | ea | 435 | ea | 1305 | 0 | 0% | 1305 | 100% | 0% | 0 | 100% | 1305 | 0% | 0% | 0 | 100% | 1305 | 0% | 0% | 0 | 100% | 1305 | 0% | 0% | 0 | 100% | 1305 | 0% | 0% | 0 | 100% | 1305 | 0% | 0% | 0 | 100% | 1305
| SANITARY SEWER |  |  |  | TOTAL | 70693.55 | 69389 |  | 1305.05 |  |  | 0 |  | 0.05 |  |  | 0 |  | 0.05 |  |  | 0 |  | 0.05 |  |  | 0 |  | 0.05 |  |  | 0 |  | 0.05 |  |  | 0 |  | 0.05
| CULINARY WATER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 8" Ductile Iron C51 Water Line | 897 | lf | 45.52 | lf | 40831.44 | 40831 | 100% | 0.44 | 100% | 0% | 0 | 100% | 0.44 | 0% | 0% | 0 | 100% | 0.44 | 0% | 0% | 0 | 100% | 0.44 | 0% | 0% | 0 | 100% | 0.44 | 0% | 0% | 0 | 100% | 0.44 | 0% | 0% | 0 | 100% | 0.44
2 | Furnish and Install 8" Gate Valve | 4 | ea | 2163 | ea | 8652 | 8652 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Furnish and Install Bends and Tees | 3 | ea | 1500 | ea | 4500 | 4500 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Furnish and Install Fire Hydrant | 2 | ea | 5305.4 | ea | 10610.8 | 10611 | 100% | -0.2 | 100% | 0% | 0 | 100% | -0.2 | 0% | 0% | 0 | 100% | -0.2 | 0% | 0% | 0 | 100% | -0.2 | 0% | 0% | 0 | 100% | -0.2 | 0% | 0% | 0 | 100% | -0.2 | 0% | 0% | 0 | 100% | -0.2
5 | Furnish and Install 1" Copper Laterals (Meter w/ box) | 16 | ea | 1660 | ea | 26560 | 26560 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
6 | Furnish and Install Air Vac Assembly | 1 | ea | 7844.57 | ea | 7844.57 | 0 | 0% | 7844.57 | 100% | 0% | 0 | 100% | 7844.57 | 0% | 0% | 0 | 100% | 7844.57 | 0% | 0% | 0 | 100% | 7844.57 | 0% | 0% | 0 | 100% | 7844.57 | 0% | 0% | 0 | 100% | 7844.57 | 0% | 0% | 0 | 100% | 7844.57
7 | Connect to Existing Main | 2 | ea | 1750 | ea | 3500 | 3500 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
8 | Clean / Flush / Test Video | 897 | lf | 1.25 | lf | 1121.25 | 1121 | 99.98% | 0.25 | 100% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25
9 | Collar Valves | 5 | ea | 435 | ea | 2175 | 0 | 0% | 2175 | 100% | 0% | 0 | 100% | 2175 | 0% | 0% | 0 | 100% | 2175 | 0% | 0% | 0 | 100% | 2175 | 0% | 0% | 0 | 100% | 2175 | 0% | 0% | 0 | 100% | 2175 | 0% | 0% | 0 | 100% | 2175
| CULINARY WATER |  |  |  | TOTAL | 105795.06 | 95775 |  | 10020.06 |  |  | 0 |  | 7845.06 |  |  | 0 |  | 7845.06 |  |  | 0 |  | 7845.06 |  |  | 0 |  | 7845.06 |  |  | 0 |  | 7845.06 |  |  | 0 |  | 7845.06
| OTHER SITE COSTS | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT
1 | Combo Street/Stop Signs | 1 | ea | 400 | ea | 400 | 0 | 0% | 400 | 100% | 0% | 0 | 100% | 400 | 0% | 0% | 0 | 100% | 400 | 0% | 0% | 0 | 100% | 400 | 0% | 0% | 0 | 100% | 400 | 0% | 0% | 0 | 100% | 400 | 0% | 0% | 0 | 100% | 400
| Slurry Seal | 992 | sy | 3.5 | sy | 3472 | 0 | 0% | 3472
2 | Mailboxes (one bank) | 1 | ea | 2500 | ea | 2500 | 0 | 0% | 2500 | 100% | 0% | 0 | 100% | 2500 | 0% | 0% | 0 | 100% | 2500 | 0% | 0% | 0 | 100% | 2500 | 0% | 0% | 0 | 100% | 2500 | 0% | 0% | 0 | 100% | 2500 | 0% | 0% | 0 | 100% | 2500
| Other Site Costs |  |  |  | TOTAL | 6372 | 0 |  | 23786 |  |  | 0 |  | 2900 |  |  | 0 |  | 2900 |  |  | 0 |  | 2900 |  |  | 0 |  | 2900 |  |  | 0 |  | 2900 |  |  | 0 |  | 2900
| Totals |  | SUB TOTAL |  |  | 432459.92 | 359361 |  | 90513.42 |  |  | 0 |  | 58373.72 |  |  | 0 |  | 58373.72 |  |  | 0 |  | 58373.72 |  |  | 0 |  | 58373.72 |  |  | 0 |  | 58373.72 |  |  | 0 |  | 58373.72
|  | 10% | CONTINGENCY ON ALL EXCEPT ROADWAY AND EMBANKMENT EXCAVATION | [5 empty] | 42209.512 |  |  |  |  | 42209.512 |  |  |  |  | 42209.512 |  |  |  |  | 42209.512 |  |  |  |  | 42209.512 |  |  |  |  | 42209.512 |  |  |  |  | 42209.512
|  |  | PROJECT TOTAL |  |  |  | ESCROW AMT |  | 132722.932 |  |  |  |  | 100583.232 |  |  |  |  | 100583.232 |  |  |  |  | 100583.232 |  |  |  |  | 100583.232 |  |  |  |  | 100583.232 |  |  |  |  | 100583.232