## Sundown Condos
2025-07-16
Site |  |  | Cost Per Unit | Total Unit Cost
Build Hammerhead Turn Around | 1 | EA | 13800 | 13800
Block Retaining Wall | 3970 | SF | 60 | 238200
Fine Grade and Proof Roll Subgrade | 16300 | SF | 0.27 | 4401
Furnish, Grade, and Compact 8" of Roadbase | 16300 | SF | 2.95 | 48085
Furnish, Place, and Compact 3" of Asphalt | 16300 | SF | 2.85 | 46455
Total |  |  |  | 350941
Sewer
Connect to Existing Sewer Manhole | 1 | EA | 7500 | 7500
8" HDPE | 1099 | LF | 65 | 71435
4' Manholes | 8 | EA | 11600 | 92800
4" Services | 12 | EA | 3100 | 37200
Total |  |  |  | 208935
Water
4" Valve | 2 | EA | 2800 | 5600
1" Taps on New 4" Water Main | 12 | EA | 1200 | 14400
1" Meter Setters with Box | 12 | EA | 2400 | 28800
1" Poly | 100 | LF | 20 | 2000
4" PVC Water Lateral | 2 | EA | 6900 | 13800
6" Valve | 2 | EA | 3400 | 6800
Fire Hydrant | 2 | EA | 5500 | 11000
Collar for Valves | 10 | EA | 800 | 8000
PRV | 1 | EA | 40000 | 40000
8" Valve | 6 | EA | 4200 | 25200
Connect to Exist. Water Main | 2 | EA | 5000 | 10000
Total |  |  |  | 165600
Storm Drain
2' x 2' Catch Basins | 7 |  | 4200 | 29400
12" HDPE | 114 | LF | 45 | 5130
15" HDPE | 535 | LF | 55 | 29425
Total |  |  |  | 63955
Subtotal |  |  |  | 789431

## Release #1
2020-03-11
Weber County Engineering |  |  | 402T190006
2380 Washington Blvd. Ste 240
Ogden, UT 84401
RE: | Uintah View Estates
Escrow Release #1
Weber County Engineering,
This letter releases the following amount from escrow for improvements installed as requested:
| Original Escrow Balance: |  | 52612.515
| Current Escrow Balance: |  | 52612.515
Approved Releases:
Grading and Paving
|  | 4x4 Sidewalk w/base | 12240
|  | Handicap ramp(s) | 1200
|  | Total | 13440
Culinary Water
|  | Concrete collars | 900
|  | Total | 900
Secondary Water
|  | Concrete collars | 450
|  | Total | 450
| Amount released this letter: |  | 14790
| Remaining Escrow Balance |  | 37822.515
Make Draft to Jeremy Jaggi he will pick it up:
HCA Investments, Jeremy Jaggi
4287 S. Harrison Blvd. Ogden Ut 84403
If you have any comments or questions concerning this letter, feel free to contact me.
Sincerely,
Tucker Weight
Weber County Engineering Dept.
Phone: (801) 399-8104