## Prologue
Prologue | Monday, August 12
Sign | Qty | Location | Notes
BRMON | 4 | Little Cottonwood Canyon Rd | at bottom near intersection of 209, 2 facing each way
BRMON | 8 | Little Cottonwood Canyon Rd | between Snowbird entrance 1 and Alta, 4 each way
Delineators | 50 | Drop at Snowbird 1 or 2 days before event- 8/12 | 50 Delineators and another 100 bases
Delineators pick up Tuesday or later. Bases we keep all week

## Stage 1
Stage 1 | Tuesday, August 13
Sign | Qty | Location | Notes
BRTU | 4 | Airport Rd | spread over 2 miles, just east of HWY 91, 2 each way
BRTU | 2 | State 23 | just north of Black Rock Rd. 1 each way
BRTU | 2 | Town of Newton Main & Center | on Main, 1 each way

## Stage 2
Stage 2 | Wednesday, August 14
Sign | Qty | Location | Notes | Message
BRWED | 2 | Town of Perry, US 89 near Center St | one facing each way
BRWED | 2 | Town of Willard, US 89 near Center St | one facing each way
BRWED | 2 | N. Ogden, on E 2600 N near N 400 E | one facing each way
BRWED | 1 | base of powder mtn road
EMB | 1 | N. Ogden Canyon Rd, near Mountain Rd | facing west | TBD
EMB | 1 | N. Ogden Canyon Rd, near N 2900 E | facing east | TBD
EMB | 1 | bottom of Ogden Cyn. East of Valley Rd | facing west
BRBlank - Wed. Plate | 2 | State 162, near State 158 | one facing each way
BRBlank - Wed. Plate | 2 | State 39 / Ogden Canyon, just above dam | one facing each way
BRBlank - Wed. Plate | 2 | State 39 / Ogden Canyon, east of 167 | one facing each way
BRBlank - Wed. Plate | 1 | far side of Trappers (Mtn. Green) | one facing south

## Stage 3
Stage 3 | Thursday, August 15
Sign | Qty | Location | Notes
BRTHUR | 1 | UT 108/1700 S | east of 3000 W, facing east
BRTHUR | 1 | UT 108/1700 S | east of 4500 W, facing east
BRTHUR | 18 | spread over route every few miles | start at Gentile/2200 W - end at top of Bountiful hill

## Stage 4
Stage 4 | Friday, August 16
Sign | Qty | Location | Notes
EMB | 1 | S. Temple near 1300 E | facing east | remove by 4:00pm on Friday, 8/16
EMB | 1 | S. Temple near State St | facing west | remove by 4:00pm on Friday, 8/16
execute same TMP as previous years
fire hall on 11th- cone line- No need for 2019
no park signs on 11th and Temple- corner of block
no park signs on University and 1300E near Reservoir Park
|  | Early Drop (Wednesday 10pm)- | Cone off all parking spaces along E. Capitol on Wednesday night | use tall delineators
Do Not cone off spots on 500 N
Do Not cone access lane on 500 N
Drop 4 Class 3 barricades at top of E. Capitol (off to side)
Drop 4 Class 3 barricades at bottom of E. Capitol (off to side)

## Stage 5
Stage 5 | Saturday, August 17
Sign | Qty | Location | Notes
EMB | 1 | 248 just east of US 189 | facing west, expect delays Sat / Sun
EMB | 1 | 248 just west of 32 outside Kamas | facing east, expect delays Sat / Sun
BRSAT/SUN | 2 | 32 in Kamas just north/south of Center St | 1 facing north, 1 south
BRSAT/SUN | 1 | Browns Canyon north of 248 | facing south
BRSAT/SUN | 1 | Browns Canyon west of 32 | facing east
BRSAT | 15 | spread over remainder of route | Do not place in Utah Olympic Park

## Stage 6
Stage 6 | Sunday, August 18
Sign | Qty | Location | Notes
EMB | 1 | 248 just east of US 189 | facing west, expect delays Sat / Sun | left from Stage 5
EMB | 1 | 248 just west of 32 outside Kamas | facing east, expect delays Sat / Sun
BRSAT/SUN | 2 | 32 in Kamas just north/south of Center St | 1 facing north, 1 south | left from Stage 5
BRSAT/SUN | 1 | Browns Canyon north of 248 | facing south
BRSAT/SUN | 1 | Browns Canyon west of 32 | facing east
BRSUN | 12 | spread over remainder of route | No access to Wolf Creek Ranch, do not place
Be sure to hit Heber City and Midway

## Inventory
4x4 Signs:
BRMON 18
BRTU 11
BRWED 7
BRTHUR 20
BRFRI 8
BRSAT 25
BRSUN 13
BRSAT/SUN 4
BRExpectDelay 11
BRTUE/WED 17
BRBlank 11
Plates:
Mon 6
Tues 0
Wed 15
Thurs 0
Friday 17
Sat 6
Sun 2
Fri/Sun 2
Tue/Wed 17