## MS PH 2 Draw Sheet
WEBER COUNTY ESCROW
Site Improvements
| The Bridges - Mountainside Phase 2 | 10 Lots | [12 empty] | Note - the Cumulative Complete needs to carry forward (add manually) to each Draw column. Then add next % complete at the next Draw
Eden, Utah
[7 empty] | As of 11/28/22 |  |  |  |  | Draw # 1 |  |  | Draw # 2 |  |  |  |  | Draw # 3 |  |  |  |  | Draw # 4 |  |  |  |  | Draw # 5 |  |  |  |  | Draw # 6
[7 empty] | CUMULATIVE $$ | % |  |  | % | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining | Cumulative | Add'l | Draw | Remaining | Remaining
| ROAD & ROW GRADING AND EXCAVATION | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | COMPLETED | COMPLETE | ESCROW AMT |  | Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance | % Complete | % Complete | Request | % | Balance
1 | Roadway Cut / Excavation | 806 | cy | 8.6 | cy | 6931.6 | 6932 | 100% | -0.4 | 100% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4
2 | Embankment Cut / Excavation | 500 | cy | 7.2 | cy | 3600 | 3600 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Import Fill For Embankment | 3500 | ton | 16.18 | ton | 56630 | 56630 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Furnish and Install 3" thick Asphalt Paving | 12222 | sf | 1.9 | sf | 23221.8 | 0 | 0% | 23221.8 | 100% | 0% | 0 | 100% | 23221.8 | 0% | 0% | 0 | 100% | 23221.8 | 0% | 0% | 0 | 100% | 23221.8 | 0% | 0% | 0 | 100% | 23221.8 | 0% | 0% | 0 | 100% | 23221.8 | 0% | 0% | 0 | 100% | 23221.8
5 | Furnish and Install 6" Road Base (includes grading) | 506 | ton | 19.27 | ton | 9750.62 | 9751 | 100% | -0.38 | 100% | 0% | 0 | 100% | -0.38 | 0% | 0% | 0 | 100% | -0.38 | 0% | 0% | 0 | 100% | -0.38 | 0% | 0% | 0 | 100% | -0.38 | 0% | 0% | 0 | 100% | -0.38 | 0% | 0% | 0 | 100% | -0.38
6 | Furnish and Install 9" Sub-base Material (includes grading) | 652 | ton | 18.2 | ton | 11866.4 | 11866 | 100% | 0.4 | 100% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4
7 | Curb and Gutter | 1003 | lf | 19.8 | lf | 19859.4 | 19859 | 100% | 0.4 | 100% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4 | 0% | 0% | 0 | 100% | 0.4
| ROAD & ROW GRADING AND PAVING |  |  |  | TOTAL | 131859.82 | 108638 |  | 23221.82 |  |  | 0 |  | 23221.82 |  |  | 0 |  | 23221.82 |  |  | 0 |  | 23221.82 |  |  | 0 |  | 23221.82 |  |  | 0 |  | 23221.82 |  |  | 0 |  | 23221.82
| STORM DRAINAGE | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 15" RCP Storm Drain | 406 | lf | 46.1 | lf | 18716.6 | 18717 | 100% | -0.4 | 100% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4
2 | Furnish and Install 24" x 48" Concrete Catch Basin | 1 | ea | 2755 | ea | 2755 | 2755 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Furnish and Install 4' Storm Drain Manhole | 2 | ea | 2755 | ea | 5510 | 5510 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Collar Storm Drain Manhole | 2 | ea | 600 | ea | 1200 | 1200 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
| STORM DRAIN |  |  |  | TOTAL | 28181.6 | 28182 |  | -0.4 |  |  | 0 |  | -0.4 |  |  | 0 |  | -0.4 |  |  | 0 |  | -0.4 |  |  | 0 |  | -0.4 |  |  | 0 |  | -0.4 |  |  | 0 |  | -0.4
| SECONDARY WATER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 10" PVC C900 Water Line | 275 | lf | 36.55 | lf | 10051.25 | 10051 | 100% | 0.25 | 100% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25 | 0% | 0% | 0 | 100% | 0.25
2 | Furnish and Install 10" Gate Valve | 1 | ea | 2500 | ea | 2500 | 2500 | 100% | 0
3 | Furnish and Install 10" Tees | 1 | ea | 954 | ea | 954 | 954 | 100% | 0
4 | Furnish and Install 10" Bends | 1 | ea | 1291 | ea | 1291 | 1291 | 100% | 0
5 | Furnish and Install 8" PVC C900 Water Line | 500 | lf | 21.04 | lf | 10520 | 10520 | 100% | 0
6 | Furnish and Install 8" Gate Valve | 1 | ea | 2296 | ea | 2296 | 2296 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
7 | Furnish and Install 8" Tees | 1 | ea | 954 | ea | 954 | 954 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
8 | Furnish and Install 8" Bends | 1 | ea | 1291 | ea | 1291 | 1291 | 100% | 0
9 | Furnish and Install 4" Drain Valve | 2 | ea | 1231 | ea | 2462 | 1231 | 50% | 1231 | 100% | 0% | 0 | 100% | 1231 | 0% | 0% | 0 | 100% | 1231 | 0% | 0% | 0 | 100% | 1231 | 0% | 0% | 0 | 100% | 1231 | 0% | 0% | 0 | 100% | 1231 | 0% | 0% | 0 | 100% | 1231
10 | Single Service Connection | 2 | ea | 1294 | ea | 2588 | 2588 | 100% | 0
11 | Double Service Connection | 4 | ea | 1968 | ea | 7872 | 7872 | 100% | 0
12 | Temporary Blow Off | 1 | ea | 1438 | ea | 1438 | 1438 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
13 | Connect to Existing Main | 2 | ea | 1046 | ea | 2092 | 2092 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
14 | Collar Valves | 2 | ea | 600 | ea | 1200 | 0 | 0% | 1200 | 100% | 0% | 0 | 100% | 1200 | 0% | 0% | 0 | 100% | 1200 | 0% | 0% | 0 | 100% | 1200 | 0% | 0% | 0 | 100% | 1200 | 0% | 0% | 0 | 100% | 1200 | 0% | 0% | 0 | 100% | 1200
| SECONDARY WATER |  |  |  | TOTAL | 47509.25 | 45078 |  | 2431.25 |  |  | 0 |  | 2431.25 |  |  | 0 |  | 2431.25 |  |  | 0 |  | 2431.25 |  |  | 0 |  | 2431.25 |  |  | 0 |  | 2431.25 |  |  | 0 |  | 2431.25
| SANITARY SEWER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 8" SDR-35 Sewer Main | 1092 | lf | 38.55 | lf | 42096.6 | 42097 | 100% | -0.4 | 100% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4 | 0% | 0% | 0 | 100% | -0.4
2 | 4" Sewer Laterals off 8" Main | 10 | ea | 965 | ea | 9650 | 9650 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Furnish and Install 4' Diameter Manhole - Precast | 4 | ea | 3813 | ea | 15252 | 15252 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Furnish and Install 4' Diameter Manhole - Precast | 1 | ea | 5159 | ea | 5159 | 5139 | 99.61% | 20 | 100% | 0% | 0 | 100% | 20 | 0% | 0% | 0 | 100% | 20 | 0% | 0% | 0 | 100% | 20 | 0% | 0% | 0 | 100% | 20 | 0% | 0% | 0 | 100% | 20 | 0% | 0% | 0 | 100% | 20
5 | Connect / Test Video | 1092 | ea | 1.5 | ea | 1638 | 1638 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
6 | Collar Valves | 5 | ea | 600 | ea | 3000 | 0 | 0% | 3000 | 100% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000
| SANITARY SEWER |  |  |  | TOTAL | 76795.6 | 73776 |  | 3019.6 |  |  | 0 |  | 19.6 |  |  | 0 |  | 19.6 |  |  | 0 |  | 19.6 |  |  | 0 |  | 19.6 |  |  | 0 |  | 19.6 |  |  | 0 |  | 19.6
| CULINARY WATER | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT | TOTAL AMOUNT
1 | Furnish and Install 8" Ductile Iron C51 Water Line | 700 | lf | 45.52 | lf | 31864 | 31864 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
2 | Furnish and Install 8" Gate Valve | 0 | ea | 2163 | ea | 2296 | 2296 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
3 | Furnish and Install 8" Tees | 1 | ea | 1238 | ea | 1238 | 1238 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
4 | Furnish and Install 8" Bends | 5 | ea | 903 | ea | 4515 | 4515 | 100% | 0
5 | Furnish and Install Fire Hydrant | 1 | ea | 5586 | ea | 5586 | 5586 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
6 | Furnish and Install 1" Copper Laterals (Meter w/ box) | 10 | ea | 1660 | ea | 16600 | 16600 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
7 | Furnish and Install Temporary Blow Off | 1 | ea | 1078 | ea | 1078 | 1078 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
8 | Install Fire Hydrant Assembly | 1 | ea | 5586 | ea | 5586 | 5586 | 100% | 0
9 | Connect to Existing Main | 1 | ea | 1895 | ea | 1895 | 1895 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
10 | Clean / Flush / Test Video | 700 | lf | 1.25 | lf | 875 | 790 | 90.29% | 85 | 100% | 0% | 0 | 100% | 85 | 0% | 0% | 0 | 100% | 85 | 0% | 0% | 0 | 100% | 85 | 0% | 0% | 0 | 100% | 85 | 0% | 0% | 0 | 100% | 85 | 0% | 0% | 0 | 100% | 85
11 | Collar Valves | 5 | ea | 600 | ea | 3000 | 0 | 0% | 3000 | 100% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000 | 0% | 0% | 0 | 100% | 3000
| CULINARY WATER |  |  |  | TOTAL | 74533 | 71448 |  | 3085 |  |  | 0 |  | 85 |  |  | 0 |  | 85 |  |  | 0 |  | 85 |  |  | 0 |  | 85 |  |  | 0 |  | 85 |  |  | 0 |  | 85
| OTHER SITE COSTS | QUANTITY |  | UNIT PRICE |  | TOTAL AMOUNT
1 | Combo Street/Stop Signs (No additional Street Sign) | 0 | ea | 400 | ea | 0 | 0 | #DIV/0! | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
| Slurry Seal | 1551 | sy | 3.5 | sy | 5428.5 | 0 | 0% | 5428.5
2 | Mailboxes (one bank) | 1 | ea | 2500 | ea | 2500 | 2500 | 100% | 0 | 100% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0 | 0% | 0% | 0 | 100% | 0
| Other Site Costs |  |  |  | TOTAL | 7928.5 | 2500 |  | 5428.5 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  | 0
| Totals |  | SUB TOTAL |  |  | 366807.77 | 329622 |  | 37185.77 |  |  | 0 |  | 23326.02 |  |  | 0 |  | 23326.02 |  |  | 0 |  | 23326.02 |  |  | 0 |  | 23326.02 |  |  | 0 |  | 23326.02 |  |  | 0 |  | 23326.02
|  | 10% | CONTINGENCY ON ALL EXCEPT ROADWAY AND EMBANKMENT EXCAVATION | [5 empty] | 35627.617 |  |  |  |  | 35627.617 |  |  |  |  | 35627.617 |  |  |  |  | 35627.617 |  |  |  |  | 35627.617 |  |  |  |  | 35627.617 |  |  |  |  | 35627.617
|  |  | PROJECT TOTAL |  |  |  | ESCROW AMT |  | 72813.387 |  |  |  |  | 58953.637 |  |  |  |  | 58953.637 |  |  |  |  | 58953.637 |  |  |  |  | 58953.637 |  |  |  |  | 58953.637 |  |  |  |  | 58953.637