## Table 1
DEV - HLD - Taylor Landing PH4 as of 2/13/2024 - Approved by Chad Meyerhoffer
Items | Qty | Units | Price per Unit | Escrow | Total Completed | Remaining Bond/Escrow
Earthwork
Earthwork - Mobilization Mobilization | 1 | EA | 16500 | 16500 | 0 | 16500
Earthwork - GPS Modeling Earthwork | 1 | EA | 1980 | 1980 | 0 | 1980
Earthwork - Cut | 6.38 | CU YD | 7.0204 | 44.79 | 0 | 44.79
Earthwork - Fill | 7052.56 | CU YD | 4.12 | 29056.55 | 0 | 29056.55
Earthwork - Import | 7978.33 | TN | 17.31 | 138104.89 | 0 | 138104.89
Earthwork - Grub Clear | 1210.79 | CU YD | 7 | 8475.53 | 0 | 8475.53
Earthwork - Subgrade Prep | 98764 | SQ FT | 0.05 | 4938.24 | 0 | 4938.24 |  | *Chad approved all of these fees to be lumped together under Earthwork 2/12/2024
Earthwork - Compaction Testing | 28 | EA | 412.5 | 11550 | 0 | 11550 |  | Included in the number is: | Sewer | 3340 | Water | 1480 | Secondary | 1480
Earthwork - Construction Water | 28 | EA | 110 | 3080 | 0 | 3080
Earthwork - Pit Run | 2765.42 | TN | 19.41 | 53676.8 | 0 | 53676.8
|  |  |  | 267406.8 | 0 | 267406.8
Concrete
Concrete - Curb & Gutter | 2706.68 | FT | 28.87 | 78141.85 | 0 | 78141.85
Concrete - Curb Tie Ends Curb & Gutter | 10 | EA | 660 | 6600 | 0 | 6600
Concrete - ADA Ramp ADA Ramps | 2 | EA | 1375 | 2750 | 0 | 2750
Concrete - Sidewalk Sidewalks | 10683 | SQ FT | 6.7105 | 71688.57 | 0 | 71688.57
Roadwork - Road Base Roads | 53521 | SQ FT | 1.15 | 61550 | 0 | 61550
Asphalt Asphalt | 53521 | SQ FT | 1.92 | 102761.74 | 0 | 102761.74
Asphalt - Chip & Seal | 53521 | SQ FT | 0.46711 | 24999.9963 | 0 | 24999.9963 |  | We have a minimum amount fo $25K but the county charges us .76 sq ft which comes to | [6 empty] | 40675.96 | This is the number that is on the budget
Asphalt - Collars Asphalt | 25 | EA | 550 | 13750 | 0 | 13750
|  |  |  | 362242.1563 | 0 | 362242.1563
Sewer | 141511.7363
Sewer - 8" Sewer Sewer | 1101.34 | FT | 48.7 | 53635.26 | 0 | 53635.26
Sewer - Sleeves Sewer | 105.43 | FT | 120 | 12651.6 | 0 | 12651.6
Sewer - Connect to existing Sewer | 1 | EA | 1380 | 1380 | 0 | 1380
Sewer - Lateral Sewer | 28 | EA | 1944.8 | 54454.4 | 0 | 54454.4
Sewer - 4' Manhole Sewer | 6 | EA | 4700.3 | 28201.8 | 0 | 28201.8
|  |  |  | 150323.06 | 0 | 150323.06
Culinary Water
Culinary - Connect to existing Culinary Water | 2 | EA | 1850 | 3700 | 0 | 3700
Culinary - 8" Water Line Culinary Water | 1402.81 | FT | 58.01 | 81377.01 | 0 | 81377.01
Culinary - Bend Culinary Water | 2 | EA | 950 | 1900 | 0 | 1900
Culinary - Tee's Culinary Water | 1 | EA | 1750 | 1750 | 0 | 1750
Culinary - Fire Hydrant Culinary Water | 2 | EA | 8085 | 16170 | 0 | 16170
Culinary - Blow Off Culinary Water | 1 | EA | 1250 | 1250 | 0 | 1250
Culinary - Gate Valve Culinary Water | 4 | EA | 2730 | 10920 | 0 | 10920
Culinary - Service Culinary Water | 28 | EA | 2284.8 | 63974.4 | 0 | 63974.4
|  |  |  | 181041.41 | 0 | 181041.41
Secondary Water
Secondary - 8" Irrigation Secondary Water | 1394.33 | FT | 55.23 | 77008.85 | 0 | 77008.85
Secondary - Double Service Secondary Water | 15 | EA | 6013.7 | 90205.5 | 0 | 90205.5
Secondary - 8" GV Irrigation Secondary Water | 1 | EA | 2730 | 2730 | 0 | 2730
Secondary - Irrigation T Secondary Water | 1 | EA | 1750 | 1750 | 0 | 1750
Secondary - Connect to existing Secondary Water | 2 | EA | 1850 | 3700 | 0 | 3700
Secondary - Blow Off Secondary Water | 1 | EA | 1250 | 1250 | 0 | 1250
Secondary - Bend Irrigation Secondary Water | 2 | EA | 950 | 1900 | 0 | 1900
|  |  |  | 178544.35 | 0 | 178544.35
Storm Drain
Storm Drain - 24" RCP Storm Drain | 168.39 | FT | 78.58 | 13232.09 | 0 | 13232.09
Storm Drain - 18" RCP Storm Drain | 964.44 | FT | 65.55 | 63219.04 | 0 | 63219.04
Storm Drain - 15" RCP Storm Drain | 423.11 | FT | 59.69 | 25255.44 | 0 | 25255.44
Storm Drain - Curb Box Storm Drain | 5 | EA | 4344.69 | 21723.45 | 0 | 21723.45
Storm Drain - Combo Box Storm Drain | 6 | EA | 7370 | 44220 | 0 | 44220
Storm Drain - Manhole Storm Drain | 1 | EA | 5855.3 | 5855.3 | 0 | 5855.3
Storm Drain - Flared end Storm Drain | 2 | EA | 2150 | 4300 | 0 | 4300
Storm Drain - Pond Retention Pond | 2453.73 | CU YD | 6.6 | 16194.62 | 0 | 16194.62
|  |  |  | 193999.94 | 0 | 193999.94
SWPPP
SWPPP - Berm SWPPP | 1457.65 | FT | 3 | 4372.95 | 0 | 4372.95
SWPPP - Porta Potty SWPPP | 6 | EA | 300 | 1800 | 0 | 1800
SWPPP - Tracking pad SWPPP | 1 | EA | 2500 | 2500 | 0 | 2500
SWPPP - Inlet protection SWPPP | 12 | EA | 300 | 3600 | 0 | 3600
|  |  |  | 12272.95 | 0 | 12272.95
Dry Utilities
Dry Utilities - Power Utilities | 3750.59 | FT | 17.6 | 66010.38 | 0 | 66010.38
Dry Utilities - Gas Casings Utilities | 326.22 | FT | 22 | 7176.84 | 0 | 7176.84
|  |  |  | 73187.22 | 0 | 73187.22
Miscellaneous
Street Trees | 56 | EA | 600 | 33600 | 0 | 33600
Street Signs | 1 | EA | 1800 | 1800 | 0 | 1800
Mailboxes | 1 | EA | 7258 | 7258 | 0 | 7258
|  |  |  | 42658 | 0 | 42658
|  |  | Subtotal | 1461675.8863 | 0 | 1461675.8863
|  |  | 10% Contingency per Chad | 146797.58 | 0 | 146797.58 | This is a new item Weber County is doing as part of the cost estimate per Chad 2/6/2024
|  |  | 10% Warraney | 146797.58 | 0 | 146797.58
|  |  | Total Bond/Escrow | 1755271.0463 | 0 | 1755271.0463
|  |  | Weber Counties number is, Chad will send me his worksheet | -1761571
|  |  | Reconcilling diff w/Weber County - Chad will send me his worksheet 2/7/2024 | -6299.9537 | The difference is because Chad seperated out the Compaction Testing for Sewer, Water and Secondary but did deduct it from Earthworks
2/12/2024 - Chad agreed to keep it all in Earthworks