## Jacquelyn Estates Escrow
2015-06-29
Weber County Engineering
2380 Washington Blvd. Ste 240
Ogden, UT 84401
RE: | Jacquelyn Estates Phase 1
Craig Standing
[5 empty] | Escrow | Released | Remaining
Weber County Engineering,
Street Signs
Combo Sign |  | 1 | EA | 150 | 150 |  | 150
Sign |  | 1 | EA | 100 | 100 |  | 100
Total |  |  |  |  | 250 | 0 | 250
Culinary Water
8" PVC Watermain |  | 600 | LF | 20 | 12000 |  | 12000
Connect to Existing Pipe |  | 1 | EA | 2500 | 2500 |  | 2500
Fire Hydrants |  | 1 | EA | 4000 | 4000 |  | 4000
Service Connections |  | 6 | EA | 800 | 4800 |  | 4800
8" Gate Valve |  | 2 | EA | 2000 | 4000 |  | 4000
Test and Chlorinate |  |  |  |  | 2000 |  | 2000
Hot Tap |  | 1 | EA | 3000 | 3000 |  | 3000
Total |  |  |  |  | 32300 | 0 | 32300
Sewer
Furnish and intall 8" PVC |  | 780 | LF | 20 | 15600 |  | 15600
5ft Manhole |  | 1 | EA | 3200 | 3200 |  | 3200
4ft Manhole |  | 4 | EA | 2700 | 10800 |  | 10800
Connect to Existing Replace MH |  | 1 | EA | 12000 | 12000 |  | 12000
Service Connections |  | 6 | EA | 550 | 3300 |  | 3300
Ring and Collar Manholes |  | 5 | EA | 800 | 4000 |  | 4000
Video and Test |  |  |  |  | 2000 |  | 2000
Total |  |  |  |  | 50900 | 0 | 50900
Grading and Paving
Import Back Fill |  | 88 | TN | 10 | 880 |  | 880
8" of Sub-base |  | 950 | TN | 16 | 15200 |  | 15200
6" Base |  | 625 | TN | 16.5 | 10312.5 |  | 10312.5
3" Asphalt |  | 330 | TN | 75 | 24750 |  | 24750
30" Curb & Gutter |  | 1005 | LF | 13 | 13065 |  | 13065
Grade Det. Pond |  | 1 | LS | 8000 | 8000 |  | 8000
Temp Turnaround |  | 1 | LS | 2000 | 2000 |  | 2000
Chip and Seal |  |  | SY | 2.5 | 14835 |  | 14835
Construct 2Ft Berm |  | 1 | LS | 1500 | 1500 |  | 1500
Total |  |  |  |  | 90542.5 | 0 | 90542.5
Storm Drain
Inlet Boxes |  | 2 | EA | 1800 | 3600 |  | 3600
4ft. Inlet Boxes |  | 2 | EA | 2000 | 4000 |  | 4000
Junction Boxes |  | 2 | EA | 1800 | 3600 |  | 3600
15" RCP |  | 87 | LF | 20 | 1740 |  | 1740
15" SDR |  | 597 | LF | 20 | 11940 |  | 11940
Connect to Exist. SD |  | 1 | LS | 1000 | 1000 |  | 1000
Outlet Structure with orifice |  | 1 | LS | 2000 | 2000 |  | 2000
Construct Swale Lines with Rock |  | 1 | LS | 5000 | 5000 |  | 5000
Total |  |  |  |  | 32880 | 0 | 32880
Secondary Water
8" Secondary water line |  | 600 | LF | 20 | 12000 |  | 12000
Service Laterals |  | 7 | EA | 800 | 5600 |  | 5600
Fittings/Valves |  | 1 | EA | 5500 | 5500 |  | 5500
Drain to Inlet Box |  | 1 | EA | 2200 | 2200 |  | 2200
Connect to Existing |  | 1 | EA | 1000 | 1000 |  | 1000
Irrigation Box |  | 1 | EA | 250 | 250 |  | 250
Hot Tap |  | 1 | EA | 3000 | 3000 |  | 3000
Total |  |  |  |  | 29550 | 0 | 29550
Landscaping
Trees; includes Garden Area (Valley Nursery) |  | 52 | EA | 60 | 3120 |  | 3120
Shrubs; includes Garden Area (Valley Nursery) |  | 41 | EA | 12 | 492 |  | 492
Grass, (The Sod Co., Meridian ID) |  | 6400 | SF | 0.32 | 2048 |  | 2048
Pergola Picnic Tables (Costco) |  | 1 | Set | 3499.99 | 3499.99 |  | 3499.99
Paver Stones (Parsons) |  | 760 | EA | 1.19 | 904.4 |  | 904.4
Sand Brown (Parsons) |  | 39.51 | CY | 51.3 | 2026.863 |  | 2026.863
Decorative grass (Valley Nursery) |  | 22 | EA | 15 | 330 |  | 330
Playground (Costco) |  | 1 | EA | 2999.99 | 2999.99 |  | 2999.99
Sign 4'X4' | (The Sign Co.) | 1 | EA | 1000 | 1000 |  | 1000
Sprinkling system (Dirks Plumbing) |  | 1 | EA | 1000 | 1000 |  | 1000
Gravel .375 minus gray (Parsons) |  | 118.5 | CY | 60.3 | 7145.55 |  | 7145.55
Mailboxes | Phase One (US Postal) | 1 | Set | 1970 | 1970 |  | 1970
Landscaping Rocks (Parsons) |  | 40 | ton | 41.1 | 1644 |  | 1644
Fence Ranch Style Phase 1 (Adam Blanchard) |  | 1090 | LF | 15 | 16350 |  | 16350
Total |  |  |  |  | 44530.793 | 0 | 44530.793
Mobilization |  |  |  |  | 6150.63 |  | 6150.63
Subtotal |  |  |  |  | 287103.923
10% Contingecy |  |  |  |  | 28710.3923 |  | 28710.3923
Grand Total |  |  |  |  | 315814.3153 |  | 315814.3153
Survey Monuments will need to be paid to Surveyors Office prior to signing of the Mylar.

## Release #1
2015-07-10
Weber County Engineering
2380 Washington Blvd. Ste 240
Ogden, UT 84401
RE: | Jacquelyn Estates Phase 1 (Craig Standing)
Escrow Release #1
Weber County Engineering,
This letter releases the following amount from escrow for improvements installed as requested:
| Original Escrow Balance: |  | 243878.6
| Current Escrow Balance: |  | 243878.6
Approved Releases:
Sewer Phs 6
8" Sewer Line
4ft Manhole
Connect to Main
Install Service Connections
Video and Test
Total
| Amount released this letter: |  | 0
| Remaining Escrow Balance |  | 243878.6
Make Draft to Craig Standing and mail to:
Ogden Utah, 84404
If you have any comments or questions concerning this letter, feel free to contact me.
Sincerely,
Chad Meyerhoffer
Weber County Engineering Dept.
Phone: (801) 399-8004
Need a pressure test for sewer
at 99ft in on video from1+34.19 to 4+39.18 there is a sharp object stressing the pipe. Has this
been looked at to see if it needs to be repaired now?
sewer line into manholes needs to be grouted.
Did not see lateral for lot 36 or lot 42 need to double check these.